Health360 – Healthcare Analytics Dashboard

Project Planning Phase — Product Backlog, Sprint Planning, Story Points & Tracking

Date: 27 October 2026     Team ID: PNT2022TMIDxxxxxx (confirm exact ID)     Maximum Marks: 8

Planning basis: Tableau healthcare dashboard with a synthetic dataset (120,000 rows, 36 columns), existing worksheets and intended Gender, Age Group, and Health Condition filters. Story points and sprint dates below are proposed estimates, not actual completed work.

# 1. Product Backlog, Sprint Schedule & Estimation

| Sprint | Functional requirement (Epic) | Story ID | User story / task | Story points | Priority | Team member / role |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | Data Access & Integration | US-01 | Connect synthetic healthcare CSV/XLSX to Tableau Desktop and verify fields | 2 | High | Project analyst |
| Sprint 1 | Data Processing | US-02 | Inspect data types, missing values, duplicate Patient IDs and condition-field encoding | 3 | High | Project analyst |
| Sprint 1 | Business Analysis | US-03 | Define and validate Total Patients KPI and patient-counting rule | 3 | High | Project analyst |
| Sprint 1 | Business Insights | US-04 | Build Total Patients and Healthcare Analysis worksheets with clear titles and labels | 3 | High | Tableau developer |
| Sprint 2 | Business Analysis | US-05 | Build/validate Stroke Cases, Diabetes and Heart Disease views | 5 | High | Tableau developer |
| Sprint 2 | Business Insights | US-06 | Build/validate Glucose Cases, Dizziness, Fatigue and Alcohol Consumption views | 5 | High | Tableau developer |
| Sprint 2 | User Interaction | US-07 | Add Gender, Age Group and Health Condition filters; verify intended worksheet scope | 5 | High | Tableau developer |
| Sprint 3 | Dashboard UX | US-08 | Arrange dashboard layout, consistent typography, spacing, colors, legends and tooltips | 5 | Medium | Tableau developer |
| Sprint 3 | Quality Assurance | US-09 | Test KPI calculations against manual samples and test single/multiple filter combinations | 5 | High | Analyst + developer |
| Sprint 3 | Documentation | US-10 | Add synthetic-data disclaimer, document KPI definitions and dashboard usage | 2 | High | Project analyst |
| Sprint 4 | Release Readiness | US-11 | Test workbook opening, layout, filter reset, no-match cases and presentation-size readability | 3 | Medium | QA / analyst |
| Sprint 4 | Delivery | US-12 | Save final workbook, capture dashboard screenshots and prepare project demonstration | 3 | Medium | Project team |

User-story framing: As a project analyst or dashboard viewer, I want to explore validated healthcare summaries and filter the synthetic records so I can compare descriptive patterns in one place.

# 2. Proposed Sprint Tracker

| Sprint | Planned story points | Duration | Proposed start | Proposed end | Completed points at end | Actual release date |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | 11 | 6 working days | 27 Oct 2026 | 1 Nov 2026 | Not yet measured | Not yet scheduled |
| Sprint 2 | 15 | 6 working days | 3 Nov 2026 | 8 Nov 2026 | Not yet measured | Not yet scheduled |
| Sprint 3 | 12 | 6 working days | 10 Nov 2026 | 15 Nov 2026 | Not yet measured | Not yet scheduled |
| Sprint 4 | 6 | 6 working days | 17 Nov 2026 | 22 Nov 2026 | Not yet measured | Not yet scheduled |

Planning note: The dates are illustrative proposed dates based on the current date, not historical or confirmed team commitments. Adjust them to your instructor/team calendar. Completed points and actual release dates must be filled only after the sprint finishes.

# 3. Velocity

Velocity = sum of story points actually completed in a sprint. Average velocity = total completed story points across completed sprints ÷ number of completed sprints. Since no completed-sprint data was provided, actual team velocity is currently unknown. Do not treat planned points as actual velocity.

For a simple planning rate, planned points per sprint ÷ sprint duration in working days gives planned throughput. Example for Sprint 1: 11 ÷ 6 ≈ 1.83 planned story points per working day; this is a planning estimate, not measured velocity.

# 4. Burndown Chart Data Template

| Sprint | Day | Ideal remaining points | Actual remaining points (fill from daily tracking) |
| --- | --- | --- | --- |
| Sprint 1 | Day 0 | 11 | 11 |
| Sprint 1 | Day 1 | 9 | 10 |
| Sprint 1 | Day 2 | 7 | 8 |
| Sprint 1 | Day 3 | 5 | 6 |
| Sprint 1 | Day 4 | 3 | 4 |
| Sprint 1 | Day 5 | 1 | 2 |
| Sprint 1 | Day 6 | 0 | 0 |

The ideal values illustrate a straight-line burn from 11 to 0. The actual values shown are placeholders/examples only and must be replaced with the team's real daily remaining work before submission.

# 5. Definition of Done

Data fields and condition encodings are inspected; data-quality issues are documented.

Each KPI has a documented definition and correct denominator/counting rule.

All nine worksheets render and have readable titles, labels and tooltips.

Gender, Age Group and Health Condition filters behave as intended.

Dashboard is tested with no filter, individual filters, combined filters and no-match selections.

Synthetic-data disclaimer is visible; no clinical diagnosis claims are made.

Workbook opens successfully and the final demonstration is ready.

# 6. Items to confirm before submission

Confirm the exact Team ID (template shows PNT2022TMIDxxxxxx), actual team-member names, sprint calendar, and whether your instructor expects historical dates from the template or a new project schedule. Replace all illustrative burndown values and unmeasured completion fields with actual project records.